## Slide 1
Activity Name
Start
Finish
Original Duration
RRReeellleeeaaassseee DDDaaatetetesss
Release Dates
CCChhhaaarrrttt DDDaaattteeesss
Chart Dates
TTTRRR222 FFFuuullllll
ZZZMMMPPP
ZZZFFFWWW
ZZZOOOBBB
 | ISD Finish |  | 06-17-21* | 0
 | ZMP |  |  | 
 | Ph. 2.5 | 01-25-21 A | 01-29-21 A | 5
 | Ph. 3 | 03-30-21 A | 04-16-21 A | 14
 | CPRP |  | 05-03-21 A | 0
 | SDRP |  | 07-01-21* | 0
 | ZFW |  |  | 
 | P2.5 Wave1 | 02-01-21 A | 02-05-21 A | 5
 | CPRP |  | 03-11-21 A | 0
 | P3 Wave2 | 03-12-21 A | 03-23-21 A | 12
 | SDRP |  | 06-24-21* | 0
 | SDRP |  | 06-27-21* | 0
 | Travel | 08-11-21* | 08-11-21 | 1
 | Ph.3 Wave3 | 08-12-21* | 08-20-21 | 8
 | Travel | 08-21-21* | 08-21-21 | 1
 | ZOB |  |  | 
 | Ph. 3 | 02-12-21 A | 03-05-21 A | 15
 | CPRP |  | 04-10-21 A | 0
 | SDRP |  | 06-03-21* | 0
 | SDRP |  | 06-05-21* | 0
25 01
08 15 22
17 24 31 07
14 21 28 05 12
19 26 02 09
16 23 30 06
January
04 11 18
February
March
01 08 15
April
22 29 05 12 19 26 03 10
May
June
July
August
ptember
2021
EAE410, 02-18-21*
EAE500, 08-26-21*
01-28-21*
02-25-21*
03-25-21*
04-22-21*
05-20-21*
06-17-21*
07-15-21*
08-12-21*
09-09-
TR2 Full
ISD Finish, 06-17-21*
ZMP, 01- 25-21 A
07-01-21
01-25-21 A
01-29-21 A
03-30-21 A
04-16-21 A
CPRP, 05-04-21 A
SDRP, 07-01-21*
ZFW, 02-01-21 A
08-21-21
02-01-21 A
02-05-21 A
CPRP, 03-11-21 A
03-12-21 A
03-23-21 A
08-12-21*
08-20-21
ZOB, 02-12-21 A
06-05-21
02-12-21 A
03-05-21 A
CPRP, 04-10-21 A
SDRP, 06-03-21* SDRP, 06-05-21*
ERAM TR2 Full. Key Sites + Supplemental Server. - Schedule Summary. Updated: 05/05/21
3 Sectors per night for Key Sites Phase 3 | Cont. Fam. +50% ZLA-ZME
Chart Main Chart Interim Release Date
Summary Milestone Phase 2.5
Phase 3 Ph.3 Wave3.
SDRP, 06-24-21*
SDRP, 06-27-21*
Ph.3 Wave3
EAE410 5/8
EAE410 6/9
EAE410 6/6

## Slide 2
2021 2022
cember January February March April May June July August September October November December January February March April May June
7 14 21 28 04 11 18 25 01 08 15 22 01 08 15 22 29 05 12 19 26 03 10 17 24 31 07 14 21 28 05 12 19 26 02 09 16 23 30 06 13 20 27 04 11 18 25 01 08 15 22 29 06 13 20 27 03 10 17 24 31 07 14 21 28 07 14 21 28 04 11 18 25 02 09 16 23 30 06 13 20 7
EAE410, 02-18-21* EAE500, 08-26-21* EAF100, 03-24-22*
04-21-22*
TR2 Full, 01-25-21 A
5-19-22*
ISD Finish, 06-17-21*
ZMP, 01- 25-21 A
07-01-21
CPRP
SDRP
ZFW, 02-01-21 A
CPRP
ZOB, 02-12-21 A
06-05-21
ZLA, 04-12-21
09-20-21
ZJX, 04-19-21
09-27-21
ZDC, 04-26-21
ZOA, 05-10-21
10-08-21
ZLC, 05-17-21
09-27-21
ZTL, 05-24-21
01-13-22
ZKC, 06-07-21
ZAB, 06-21-21
01-31-22
ZSE, 07-05-21
ZDV, 07-05-21
02-11-22
ZME, 08-02-21
02-18-22
ZAU, 08-16-21
03-25-22
04-01-22
04-08-22
04-15-22
05-06-22
06-03-22
ERAM TR2 Full. 20 sites. - Schedule Summary and Phases Details. Updated 05/05/21. 3 Sectors per night for Phase 3. Cont. Fam.+50% ZLA-ZME.
Install Teams Assigned.
Summary Chart Main Chart Interim
Release Date Milestone
ILT
Cntr. Fam. Phase 1
Phase 2
Phase 2.5
Phase 3 Ph.3 Wave3
Parts Reclam.
06-03-22*
SDRP
SDRP
CPRP
08-21-21
01-28-21* 02-25-21* 03-25-21* 04-22-21* 05-20-21* 06-17-21* 07-15-21* 08-12-21* 09-09-21* 10-07-21* 11-04-21* 12-02-21* 12-30-21* 01-27-22* 02-24-22* 03-24-22*
11-16-21
11-18-21
12-14-21
ZID, 01-10-22
ZBW Virtual Site Survey, 04-15-21 A
ZHU Virtual Site Survey, 04-15-21 A
ZMA Virtual Site Survey, 04-15-21 A
ZNY Virtual Site Survey, 04-15-21 A
ZMA, 11-01-21
ZHU, 10-18-21
ZBW, 10-11-21
ZNY, 11-30-21
Ph.3 Wave3

## Slide 3
EAF100 System Release Path
2021 Q2
Updated: 4/20/21
EAE410
2/18
KS
4/20
Nat’l
SW PR
Cutoff
5/18
2021 Q3
2021 Q4
2022 Q1
8/23
KS
2021 Q1
2022 Q2
SW
Merges #1
3/23
5/24
Natl
3/24
KS
OE
Complete
3/19
Deliver
Nat’l TIs
4/20
EAE500
EAF100
EAF100
HW Engineering
SSM Dev for HW
SW Development
SW Merges #3
10/5
OE Start
Integration
2/16
I&T CRV / Regression
OE Final Runs
3/7-3/14
OE KS
2/22
SW
Merges #2
4/27
CRV KS
DC FS
9/28
OLC Need Assessment
X/XX
Issue Final
6100X
X/XX
Review SLE EBP
X/XX
Site Support
Keysite Exit
3/24
Nat’l Release
5/24
Keysite
Conduct
ERAW
Closure
10/19
Adaptation
AOT Brief
X/XX
6100/OLC
Adapt Testing w/ FAST
X/XX
SSM Validations
Validate OLC
Validate OLC
Ops Eval / Enterprise Regression
Validate OLC
CRV Complete
DC FS
10/26
CRV KS
ES3
12/28
CRV Complete
ES3
1/25
Final Regr,
PRV Complete
3/19
Keysite SW Dependencies:
Operational on EAE500 (Site)
Operational on RHEL 7.9 (Site)
EAF100 Site Exit Brief complete (AJM-25)
EAF100 SW installed in TTL (Site)
AT/TO Training briefing (AJM-21)
OE Test Prep
AT SIG
Briefings
2/19
AOT/NAT Strategy
Strategy Planning
Keysite Test Strategy Brief
2/10
TI Manuals
TI Baseline
Opened
12/3/19
Deliver Draft TIs
2/XX
Deliver
KS TIs
3/24
Quote for
Controller Cards
TBD
Order
Controller Cards
TBD
TI Stakeholder Impacts
TI
Validation Complete
1/20
SAG Exit
3/22
Safety Panel
X/XX
Training
Safety / SRM
Safety Panel
X/XX
SW SRM to sign
3/18
AT/TO/SLE
eLMS Posting
X/XX
Final
SLE EBP Delivery
3/3
Install HW @ TC Labs
TO Final Runs
3/11
Issue Draft 6100 CHGX
X/XX
6100 Development
Doc
Dev
3/4
EAE410
TI Validation Readiness Review
1/7
TO OE
Initial Look
1/20
Final
RCT
Delivery
2/24
Final
AT EBP Delivery
2/23
Start Development
8/9
H/O draft TIs to Training
4/XX
TO RCT
Storyboard
Review
12/9
Keysite Considerations
5/1

## Slide 4
ERAM Release Plan
Q1
Q2
Q3
Q4
Q2
Q1
Q3
Q1
Q4
Q2
Q3
2021
2022
2023
System Releases
EAF100
3/24/22
DC-FS (~55K SLOC)
ES3 (~18K SLOC)
EAF200
9/8/22
NavCan (~11K SLOC)
ES3 Network (~3K SLOC)
DC-FS (~3K SLOC)
QP Draw (SIG 1721A)
CSS-Wx (SIG 2001)
EAE500
8/26/21
ES3 Network (SIG 1899A)
RHEL 7.9 (SIG 1988)
IS Tailswap issue (SIG 2009)
Approach
Near term releases to support critical sustainment content to avoid realization of sustainment & performance risks
ES3 and DC FS delivered in EAF100 in March ’22
Nav Canada delayed to fall ’22
Risk mitigation: FS hard tie-off can be implemented in EAF100 if COVID impacts continue
EAE410
2/18/2021
Test Assumptions
5 SMEs starting 2/15/21, 7 SMEs starting 5/10/21, and 9 (full) SMEs starting 6/1/21
Will meet FAA COVID requirements adhering to CDC recommended precautions and OSHA 3990-03 guidelines
V3.4 4/8/21
Q4
EAF300
3/16/23
EAF400
8/17/23
TR2 Keysite
Data Comm Initial Services Waterfall (Re-planning)
ES3-ESS Waterfall
TR2 Waterfall
NAV Canada Infrastructure
NAV Canada Auto Handoff Waterfall (Re-planning)
Data Comm Full Services Waterfall (Re-planning)
Deployments
OS
RHEL 7.6
OS
RHEL 7.9
ES3 (~22K SLOC)
EE2 (~4K SLOC)
TO 140/ADS-B (~4K SLOC)
TDM-IP (~12K SLOC)
EE2 (~9K SLOC)
ES3 (~3K SLOC)
Offshore (~2K SLOC)
NavCan Interface (SIG 1814)
Support Workstation (SIG 1891)
RHEL 7.6 (SIG 1938)
DC IS content