## Slide 1: What are we working on?

## Slide 2
ERAM System Release Schedule Scorecard
= Complete
= Planned
= At Risk
= Schedule Impact
ERAM Releases | Key Site Ship | National Ship | Primary Content
EAE300 | EAE3005l - 10/2/19 EAE3005m - 10/25/19 | EAE3005n - 11/25/19 | ERAM/DataComm ERs
EAE301 | N/A | 1/24/20 | TR2 Field Fix
EAE302 | N/A | EAE30201 - 02/19/20 | DC/TR2 Field Fix
 | EAE30204 Target Site – 5/4/20 | EAE30204 – 6/4/20 | AIM process/SAA issue
EAE310 | EAE3100e - 2/26/20 | N/A | SBA/Data Comm ERs
 | EAE3100g – TBD | TBD | 
EAE320 | 5/28/20 *Working | N/A | TR2 Trackball – TTL only
EAE330 | 8/xx/20 *Working | TBD | TR2 Off Angle Viewing, Active Borders, & Trackball fixes
EAE410 | 11/5/20 | 1/5/21 | NAV Canada / DC
EAF100 | 2/18/21 | 4/20/21 | DC Full Services
EAF110 | 6/24/21 | 8/24/21 | DC Full Services IOC
EAF200 | 10/7/21 | 12/7/21 | DC Full Services Waterfall/NAV Canada Automated HandOff

## Slide 3: TR2 Assessment – EAE320/330 Program Plan (*** DRAFT ***) Active Borders, Off-Angle Colors, and R-Pos Trackball (HW/SW)
I&T (A.Borders & R-Pos Trackball)
SW Updates
SE PRED Updates
I&T
SE SIG Development
Check / PC /
Lab Installs
SE PRED Development
SW Development
SW Development
I&T
4/1
5/1
6/1
7/1
8/1
9/1
SIG 1976 – Active Borders
(A217874, A217607)
HW CR 1602 – IHSE KVM FW
(A220088 / E88350)
PRED 4200 – R-Pos TB Cursor Speed (SW / Gold)
(A217585 / E87962)
ETO
6/26
8/13
ETO
3/25
IHSE FW Release
Check / PC /
Lab Installs
4/10
4/20
Release SSM Develop,
Dry Run & Validate
Request EIZO FW Update
EIZO FW Update
Dev & Ship
Insp Closed
SE PRED Development
5/6
SSM-358
Update
Receive Rev B
R-Pos TBs
4/3
Check / PC /
Lab Installs
EIZO UHD
Update
via SSM
TTL
Install
Ops
Testing
TTL
Testing
8/20
Ship *
CE Approval
Peer Review
5/29
5/15
KeySites
ETO
6/18
7/16
8/13
SW Development (same baseline as Active Borders)
SE PRED Development
ETO
PRED 4203 – TR2: R-Pos UHD
Monitor Display Color Issues
(A218655 plus more)
SIG Closed
7/10
6/5
EAE320
(TTL Only)
6/26
* Pre-Req:: Requires Linux R-Pos TTL to start at Keysite (planned Fallback)
ZFW – 1 TTL / 3 Ops, 1 SOC. 1 TMU
ZMP – 1 TTL / 2 Ops, 3 TMU
ZOB – 0 TTL, 1 MOC/SOC / 1 Ops
6/19
PRED 4189 – R-Pos TB Replacement (HW)
(A218853 / E88483)
9/10
Key FAA / Task Team Dates (in BLUE)
6/1 – WJHTC Labs Available
7/10 – FAA Ops Eval Start based on KS
Off-Angle Color Evaluations (Factory)
6/1-6/5 – Task Team Eval #1
6/15-6/19 – CHI / HF Team Eval
7/6-7/10 – Task Team Eval #2
Gold / R-Pos TB Evaluations (KeySite TTL)
5/28-6/8 (tent) – Task Team Eval #1
6/18-6/26 (tent) – Task Team Final Eval
TTL Fixes
6/12
TTL
Install
TTL
Testing
Feedback
Task Team
Eval #1
Task Team
Final Eval
TTL
Testing
Feedback
Task Team Eval #1 (proto)
CHI / HF Team Eval (proto)
Task Team Eval #2 (SW)
EAE330
(Ops)
KS
7/10
(TBD)
7/22
I&T (Colors)
Early SW Download
Informal I&T
TTL
LOA
4/22
Labs Updated
w/ KVM FW
& R-Pos TBs
SSM-327 Update,
Dry Run & Validate
Merge
SW
5/21
Retrofit
Instructions
R-Pos TB and
KVM FW Install
via SSM
NASD / Chart Dates
Ops Eval
TTL
LOA
Ship5/XX
Ship
Ship

## Slide 4: What are we working on
Sustainment 2 Keysite (ZFW, ZMP, ZOB) Reversion Back to BARCO monitor (if required)
  Restores the legacy 20” x 20” Monitor at the RPOS
  Was the highest priority according to the sites (Weather)
  Leidos installation team with Fed. QRO and site Tech Ops support. Minimal AT impact.
  Only completed at ZOB before the shutdown
  ZMP/ZFW may still want reversion before stepping up to next software releases
Sustainment 2 Keysite Phase Greenlight, Phase 2 and Phase 3 + ISD
  Failure to move forward and complete impacts supply of critical NAS components (controller processor and display)
  Dependency on software (EAE320) delivered to keysites so AT can evaluate mitigations for 43” UHD Monitor and trackball changes
  With AT approval of 43” Monitor corrections, installation of Phase 2 and Phase 3 can complete at keysites and recovery of legacy assets can begin
  Current projections predict less than one year supply by Feb 2021. Best scenario schedules complete Phase 3 in Feb 2021.
  Large Leidos installation team with Fed. QRO and site Tech Ops support. Air Traffic familiarization in TTL most likely required.

## Slide 5: What are we working on
Supplemental Server Migration
  Servers installed at keysites (ZFW, ZMP & ZOB), no operational applications on servers yet
  Potentially complete at FAAAC first!
  Replace the legacy Conflict Probe Process (CPRP) and Surveillance Data Process Servers (SDP)
  Completion of migration will allow removal of legacy servers to mitigate sustainment risk (spareout in 2024), however performance issues of legacy servers are also a concern
  Migration is performed via SSM, changes in adaptation/configuration on chart date and done by facility personnel (Tech Ops and FAST). No impact to Air Traffic
  Needs to be accomplished at keysites prior to Sustainment 2 In-Service Decision (Mar 2021?)
Supplemental Server Deployment
  Split from Full Deployment display path installation when monitor issues stopped work
  Besides keysites, 6 ARTCCs completed installation before Coronavirus halt to travel
  Operations migration to servers (see above) prior to ISD may require approval by AJW-0
  Small Leidos install team with Fed. QRO and local Tech Ops support, no Air Traffic impact
  Remaining 11 ARTCCs can continue as separate deployment or be recombined with Full Deployment display path

## Slide 6: What are we working on
EAE400/410 – NAVCANADA Deployment
  Changes communication interface between ARTCCs and NAVCANADA in preparation for Controller enhancements in EAE200 (Fall 2021)
  Interface changes complete and tested. Software in EAE400, originally scheduled for April 2020, would have changed data flow between US and Canada
  EAE400 to merge into EAE410 and deliver in fall 2020
  Low risk to NAS; APB Milestone was missed. Resumption will require coordination with NAVCANADA to reschedule
  Changes are via SSM, site Tech Ops only. No AT Impact.
D/A Conversion to Early D Config (Risk 175)
  Newly identified mitigation to sysplanar board risk; recovers a set of up to 226 P52 processors earlier from the field by installing the new ML-30 processors in D/A consoles in a configuration similar to Early D deployment (not final Full Deployment configuration)
  The more likely Phase 3 Install pushes past Feb 2021, the higher a priority this mitigation becomes
  Requires a fix in a software delivery, packaging in EAE310 (late summer 2020?)
  Deployment can occur with Supplemental Server installation (assuming software fix uploaded)
  Leidos contractor installation team (size can be varied) with Fed QRO, SLE and local Tech Ops Support. Impacts AT during night shift installation activities.

## Slide 7
TTL GPWS Processor Swap out (Risk175)
Intellistation MWS Replacement (Risk 199)
  Dependent on EAE410 (also for ASA Hardware)
ESSP Server Processing Memory Upgrade
LINUX OS upgrade
  Dependent on EAE410 (Fall 2020)
  Prereq to EF100 (Spring 2021)
AIX R POS Memory Upgrade – EAF100? (Risk 252)
EAF300/ES3 Keysite Planning